## Sheet1
Ticket No	Gta02 Major issues	Status
1640	[Audio] Improve overall audio experience in ASU	Better-yet to be tested
1805	SD card corruption with 2008.8
1662	[GSM] not working properly after x hours of usage
1691	[Qtopia] qpe crash happened after flash the new image
1722	[GSM] should able to make a phone call in X minutes after booting up	Not complete
1789	2008.8 screen blanks and refuses to wakeup	Not complete
1888	[Setting] can't connect to network via wifi	Deferred
1841	white screen of death (WSOD) after resume	Not complete
2110	[Installer] the arrow to go back to previous page was gone	Not complete
69	Speed up System Initialization	Not complete
1991	[Suspend] unable to suspend, just stay black screen after wake up by power button from suspend	Not complete
1158	Charging stops even while connected	Not complete